## Slide 1: It’s not all about the tool!
Having both worked on large Business Change Programmes over the last 25 years, we will talk about how there is a need for flexibility in terms of Programme Governance, depending on the scope of the Programme, the type of organisation, and the nature of your Sponsors and Stakeholders..
It is never a ‘one size fits all’, but there is always a minimum level of Programme Governance required. Successful Programmes will always have a great Team, People, and Communications, and appropriate governance. . A minimum level of governance, and ‘less is more’ approach to ongoing Programme Control has to be the start point for the majority!
Programme Control

## Slide 2
    …‘Tools’ in relation to Programme Control?
      Reliance on an Enterprise PPM Software Solution to deliver successful Change Programmes
    What do we mean by Enterprise PPM Software Solution?
      Approximately £100k Plus investment
      Manages all projects in an Organisation end to end
      Integrates with all other Business Systems (HR, Finance etc)
  What do we mean by…

## Slide 4
    Try to develop into a Project Maturity that is a step too far (and possibly not required)
    Engage with the whole business to develop requirements
    This leads to only an e-ppm solution meeting the requirements resulting in:
      Investing heavily (cost and time) and not realising the benefit, using minimum functionality, and only being used by resources with advanced level Project Management skills
      Long lead times to implement across the whole organisation that the requirement has changed by the time implementation has completed
      The journey of gathering requirements, selecting a solution, developing the business case fails at one of the stages – back to manual processes
    Develop ‘in house’ because they’ve already got the license!
    A solution that will not realistically fit the different Business Change Programmes in the organisation
  Common mistakes by the majority
  Disclaimer - Understand some Project driven industries require e-ppm solutions, but the majority don’t!

## Slide 5
  Why am I here?
    Opportunity to pass on my views and experience of delivering major programmes over many years to my clients
    Frustration of working with my peers and the emphasis and time they invest on using complex tools to manage and communicate programmes of activity
    Share my approach and priorities when I start any new assignment
    Explain why the tool we decide to use is not, and should not be a major factor in delivering a successful outcome

## Slide 6
  What are my priorities at the start of a new programme?
    Identify and appoint the Project Managers based on their:
      Ability and knowledge
      Sector experience
      Fit with the culture and values of the client organisation
      Fit with the nature and style of their stakeholders
    Establish a relationship with my stakeholders and sponsor
      Understand their style and approach
      Recognise their priorities
      Establish a “contract” for delivery and deliverables

## Slide 7
  What are my priorities at the start of a new programme?
    Develop a communication strategy based on:
      The organisation’s style and values
      The sponsors requirements
      Agreeing the minimum level of communication to satisfy the above
    Establish a fit for purpose governance model based on
      The organisation style and values
      The sponsors requirements
      A realistic view of how much time is available and required to maintain control

## Slide 8
  What are my priorities at the start of a new programme?
    Identify the tool or tools we will use to manage the programme
      Support the Governance model, not drive it
      Simplify the Programme control process
      Improve quality of Project meetings (discuss exceptions not status)
      Demonstrate a Professional approach with Sponsors/Stakeholders

## Slide 9
Chart: 
| Identify PM's | Relationship with Sponsor | Communication Strategy | Establish Governance | Identify and Brief Programme Management Tool
Priorities at the start of a new programme | 20 | 35 | 20 | 20 | 5
Identify PM’s
Identify, populate and brief programme management tool
35%
20%
5%
20%
20%

## Slide 10
  My experience
    I have to get the programme established as quickly as possible, therefore:
      I do not spend any time deciding which tool I should use to manage the programme
      I do not spend any time training or briefing my project managers on how to report at programme level
    My project managers are tasked with managing their individual projects with the necessary and appropriate rigour and attention to detail, using whatever tools they deem necessary or are comfortable using (Excel, MSP etc)
    I am tasked with providing a simple and consistent summary of the programme status for the sponsors

## Slide 11
  My experience
    One report has always been sufficient to achieve this goal, covering:
      Achievements and targets for next period
      High level milestones
      RAG status of each workstream / project
      Red risks and issues
      Decisions required
    I have never encountered a sponsor who has had to request more detail

## Slide 12
  Programme / Project – 1 Page Summary Report

## Slide 13
  Programme - RAG Status Report

## Slide 14
  What are we saying so far?
    In the real World:
      Majority of successful Business Change Programmes rely on great people, communications and governance
      Implementation of, or enforcement of a ‘rich in functionality’ tool will not work in most instances
      Engaging the best team to deliver means they need flexibility to ‘do it their way’, at work stream/project level
      There is ALWAYS a requirement for quality / timely Project Reporting, keep it simple and that’s a generic requirement!

## Slide 15
  What are we saying so far?
    In the real World:
      And if you automate that element, then:-
        Real time reporting
        Reduction of manual effort
        Better quality meetings – discuss the exceptions, not the status

## Slide 16
    Went live 2002 – lessons learnt from the Year 2000 Programme
    To meet specific requirements:-
      Achieve consistency, consolidation and aggregation across Business Change Programmes
      Automation and real time reporting, reducing time spent by Project Managers and Administrators
      Supporting the minimum level of Programme Governance, specifically in terms of reporting periodic status
      Simple enough for all organisational departments to utilise (not just IT and the skilled Project Managers)
  ProgrammExpress – Portfolio, Programme and Project Reporting

## Slide 17
Simple
Complex
Project Manager
(Skilled)
  KISS – The Key to Engagement
Engaged
Switched OFF
Project Manager
(Business/Subject Matter Expert)
Programme Manager
Project Director
Programme Director
Business Change Director
PMO Director
PMO Manager
Stakeholder
Sponsor
CIO
Sponsor
IT Director
CEO

## Slide 18
Simple
Complex
Project Manager
(Skilled)
  KISS – The Key to Engagement
Engaged
Switched OFF
Project Manager
(Business/Subject Matter Expert)
Programme Manager
Project Director
Programme Director
Business Change Director
PMO Director
PMO Manager
Stakeholder
Sponsor
CIO
Sponsor
IT Director
CEO

## Slide 19
Simple
Complex
  KISS – The Key to Engagement
Engaged
Switched OFF
Project Manager
(Skilled)
Project Manager
(Business/Subject Matter Expert)
Programme Manager
Project Director
Programme Director
Business Change Director
PMO Director
PMO Manager
Stakeholder
Sponsor
CIO
Sponsor
IT Director
CEO

## Slide 20
  Home Screen – Total View

## Slide 21
  Home Screen – User Update View

## Slide 22
  What is our Key Message?
    Aspiring to Enterprise PPM solutions may never materialise due to time and cost, and may leave you with manual solutions
    Quality Project Governance is fundamentally important but:-
      Be flexible
      Don’t over engineer
      Get the balance right
    Let Project Managers do what they do for managing their projects in terms of tools and systems
    You need a solution at Portfolio and Programme level, and the simpler the solution, the more engagement across the organisation at all Project Maturity levels, the more multiple Business Change Programmes can adapt to, more chance of the ‘Big Picture’ being available
    Tools and Systems are a small, but essential, part of the success of a Programme/Project!!

## Slide 23
Q&A
Further Discussion – Stand 128